Free Up Your Life

(East London Mentoring Project)

# Index

|  | Page |
| --- | --- |
| Foreword by Richard Rieser | 2 |
| 1. A Pen Picture | 4 |
| 2. Project Structure | 4 |
| 3. How the Project was delivered | 5 |
| 4. Activities in the Mentoring Sessions | 7 |
| 5. Parents | 14 |
| 6. School Staff | 14 |
| 7. Promotion of Inclusion in Schools | 16 |
| 8. Conclusions and Recommendations | 16 |
| Appendix - Timetable of Activities | 23 |

Disability Equality In Education

Unit GL, Leroy House

436 Essex Road

London

N1 3QP

Registered Charity No: 1055287

## Foreword

## to

Free Up Your Life

End of Project Report

For many years disabled young people have been isolated and segregated in education that has had an inevitable impact on their self-image.

In the last 25 years there has rightly been an increasing emphasis on integrating disabled students into mainstream schools. Now the SEN and Disability Act enshrines these moves in a rights framework for disabled pupils and students. Recently teachers and other staff have tended to focus on including disabled students in the curriculum and to a lesser extent the social life of the school. This is what the Government would call inclusion, and DEE spends much time training staff across the education system- more than 15,000 in the last three years. Our training is based on a rights based approach, which views disability as a social construct created by barriers of attitude, environment and organisation. Having a significant impairment leads to this exclusion, but it is not the cause.

What is often left out of this formulation is how disabled young people feel about themselves and how they should make sense of living their lives as disabled people. This pioneering project begins to open up these issues by providing disabled adult mentors to work with groups of young disabled people to develop self esteem and life skills. Often just being there - as confident, independent and professional disabled adults - opened up new horizons for the young people.

The project has thrown up a wealth of experience and insights about how to implement this process. This was just a pilot, but we already know (as do the teachers, staff and young people who were involved in this project) that all schools need such mentoring projects involving successful disabled adults as role models and mentors.

Disability Equality in Education would like to thank

- The Department for Education and Skills for funding this project

- the London Boroughs of Hackney, Tower Hamlets, Newham and Camden.

- We would particularly like to express our appreciation to the pupils and staff of East Lea, George Green, Langdon, Royal Docks, South Camden Community Secondary Schools for the collaboration and support that has made this project possible.

- Thank you to Christine O’Mahony for her patience, skill and determination in making this happen,

- and thanks to our mentors.

It is our great hope that the usefulness of such mentoring schemes will be taken up by the statutory sector, so that young disabled people can be empowered and equipped to live a full and inclusive life.

Richard Rieser, Director of DEE,  March 2003.

##### Free Up Your Life

##### End of Project Report – March 2003

##### 1.  A Pen Picture

1.1 In May 2002, Disability Equality in Education (DEE) won a £30,000 grant from the DfES to set up a pilot mentoring project for disabled young people in mainstream schools in partnership with the education authorities in three London boroughs.

1.2 It was agreed that there would be two groups set up in each borough.  Each group was to meet eight times before the end of March 2003 and activities would be loosely based around a curriculum that includes the following.

- Rights and Disability

- Getting about – How?  Where?

- Getting Direct Payments and managing money

- Going out /going on holiday

- Dealing with bullying and name-calling

- Getting a job or further training – getting access to technology

- Living independently – getting accommodation

- Relationships with other people

1.3 Young disabled people were encouraged to involve their non-disabled friends in the groups so that a clearer understanding of disabled issues would emerge for them.

Many of the young people involved in the groups were labelled as having learning difficulties.  Some had physical impairments and the groups spanned a wide range of access and communication needs.

##### 2.  Project Structure

###### 2.1 Management

The Project was managed by Disability Equality in Education, via the Director, Richard Rieser, and the Trustees of Disability Equality in Education.  Reports were made to the Director and Trustees on a regular basis, including a written Interim Report in December 2003.

###### 2.2 Co-ordinator

A Project Coordinator was appointed to work on a 40-day contract from June 2002 – March 2003.  The job description included:  getting the project off the ground, contacting schools and educational authorities, appointing, supervising and supporting mentors, setting up mentoring groups in conjunction with the schools and overseeing the project generally.

###### 2.3 Mentors

Fourteen disabled mentors were appointed but, in the event, only eight were able to take up the work.  They came from a variety of backgrounds including teaching, youth work, community work, People First, etc.  Two young mentors were new to the work but had the experience of being disabled in local special and mainstream schools.  They also had experience of youth work.   All mentors had undergone the DEE Training the Trainers course, which focuses on issues around disability and inclusion.  Three training sessions were offered for mentors: one looking at the role of mentor and building relationships with young people; one looking at the proposed curriculum and how we could achieve it; and one looking at what we have learnt from the project.

##### 3.  How the Program was delivered

  - We started Free Up Your Life with conferences in two London Boroughs for young disabled people and their non-disabled friends.  The planned conference in a third borough had to be cancelled due to a transport strike on that day and the low take up from schools.   The Conferences were used to explain the project and included performances by disabled artistes.  (Graea Theatre premiered their new play “The Trouble with Richard” at one Conference.)  We also had drumming and story telling workshops, as well as discussion groups at both.    We then went on to set up five mentoring groups in three different schools.  The groups started meeting from the end of October 2002.

  - We approached a sixth school in January 2003 because we wanted to try out a different model of working with young people for comparison purposes.   They responded enthusiastically and we arranged for a mentor to work one-to-one with two young people at the school, addressing the same issues as were addressed in the group sessions.

##### 3.3 Number of schools contacted:  34

Borough 1  - All secondary schools		12

Borough 2 - All secondary schools			12

Borough 3 – All secondary and

- one special school 			  9

Borough 4					 		  1

3.4 Number of young people contacted: 79

Conference 1:			  				30

Conference 2:				  			45

Borough 3:  							  2

Borough 4:  							  2

##### 3.5 Young people who joined mentoring sessions:  38

School 1:				  				24

(two groups of 12)

School 2:   					                  8

School 3:              		        			          4

School 4:	          						  2

##### 3.6 Number of Mentoring Sessions offered:  64

We met roughly fortnightly with disabled

young people in mainstream schools

for eight sessions per group.

##### 4.  Activities in the Mentoring Sessions

Each mentoring group devised its own specific activities within the limits of the programme as outlined in section 1.2.  Each group differed in size, make up, personalities, impairment issues, and goals.  Lead mentors negotiated plans with the groups and delivered the programme in a range of ways that included using: role-play; images; music; games; visual expression; discussion; and one-to-one sessions.  At one School, a mentor developed a Snakes & Ladders style game that illuminates the barriers to inclusion and supports disabled young people’s encounters in home life, school life and social life.

###### 4.1  Young People’s Dreams and Aspirations

At two schools, art sessions were used with young people with learning difficulties to develop visual images of their lives and aspirations.  Extensive work was done around the transition from school to college or work.   Starting with an image of ‘hopes and dreams’, we were able to elicit the life aspirations of young people with learning difficulties and talk with them about their futures.

“The young people were very keen to talk about their futures.  Some have already got transition plans in place; others seemed very hazy about what they are going to be doing after the end of school.  One young person burst into tears and said she was very frightened of leaving, she thinks she will not have any friends and will not be going out at all.  This led to a discussion of friends outside school.  None of the young people see friends from school when they are at home.  Social activities seem to be contained within the family with most of them quoting activities with a ‘cousin’ as the fun things they do.  All but one of the young people saw themselves as continuing to live at home in the future.  One confessed she would like to live with her boyfriend before marriage but she is not planning to tell her parents.”

Mentor

“Some things have been very exciting for them to look at, difficulties they have about leaving school and going into the world of work, learning to drive, etc.”

Teacher

###### 4.2 Independent Travelling

At one school, a wheelchair user wanted to think about being able to drive.  He had not been aware that he could become an independent car user.  His mentor took him out to her car to demonstrate how she got in and out of it.  Up to that point he had assumed that he would always be dependent on family members for support with travel.  The mentor explained about Motability and the Disabled Living Allowance.  It was very important in this instance that his mentor was disabled.  Having a wheelchair-using role model who is professional, earning good money, and driving herself around raised the possibility of an independent future for him.  It is doubtful that a non-disabled person giving the same information would have had so profound an effect on his self-image.

###### 4.3 Bullying

A lot of work was done around bullying.   One group used the transcript of the Graeae Play “The Trouble with Richard” to role-play issues around bullying and discrimination towards disabled young people.  This was early on in the programme.  A later session on bullying brought forth more detailed descriptions of bullying and information about bullying:

“Before splitting into boys and girls, two of us admitted to having been bullies at school.  We described what we did and what were the outcomes.  We asked if anyone in the group had ever bullied someone and one person said he enjoyed following people and making them frightened.  The group (most of whom had been at Special School previously) said that there was far less bullying going on their mainstream school than there had been at Special School.  No-one had ever felt bullied personally, although they had seen others being bullied.  They were full of praise for their teachers and said that they had never experienced bullying teachers in the mainstream, although this was common in the Special School they had attended.

In the boys’ group the discussion led to an understanding of what might be the causes of bullying, but no admissions of being bullied.  The girls’ group discussed the different ways girls bully and boys bully and agreed that girls tend to pull hair, use bad words and hurt people’s feelings rather than kick and punch like boys do.  One wheelchair user said she had felt bullied when she first came to the school as other children pushed her chair around and demanded rides on it.  However, the teachers had explained about her personal space and she no longer had that problem.”

Mentor

###### 4.4 The importance of Mobile Phones

We used ground rules agreed by the young people as a basis for discussion of a wide range of issues, including: having girlfriends/ boyfriends; money; friendships; being treated respectfully; not telling each other’s secrets; etc.   An interesting way of getting at issues important to young people was to develop a discussion around the use of mobile phones.  Issues that came up included:

- Relationships (girlfriends/boyfriends),

- Friendships (who calls who and why);

- Money (who pays your mobile bill, how do you handle money negotiations with parents);

- Crime (phone mugging, bullying by the phone, safety on the streets, etc.)

###### 4.5 Activities Outside School

It was clear that most of the disabled young people we met in one school led very isolated lives outside.  None of them met friends at weekends, except when they accidentally ran into each other at a community project for disabled young people.  This was never pre-arranged or organised, it just happened.  It was clear that these young disabled people are having a markedly different experience of teenager hood than their non-disabled peers.  They all agreed they loved to shop, but none had ever been on a shopping trip with friends.  One said that she had to go with her mother and this was a problem because her mother’s taste was very different from hers (old-fashioned).  She would prefer to go with young friends who shared her tastes but this was not possible.

###### 4.6 Discussing Relationships and Sex

# We talked about relationships a lot.  They were almost all interested in having a sexual partner and in developing long term relationships.  The older young people (16+) tended to have a romantic view of relationships, expecting to meet ‘the one’, get married and have children at some point in the future.  However, the younger young people (14+) at another school saw it more crudely in terms of sexual gratification and had less perspective on the right personality in a partner or on being in love.  We talked about the models they had for love, marriage and romance, asking them questions about older siblings’ relationships, parents’ relationships, etc.  This was important as their expectations were affected by their cultural backgrounds as well as by the fact of being disabled.  Most of the young people were working class and/or members of ethnic minority groups.  It was important that mentors did not impose white, middle-class or euro-centric values on their experiences and aspirations.

“This was a smaller group than usual and this led to a more intimate atmosphere that facilitated lots of discussion. What was remarkable was that it was so relaxed.  Although we had intended to split into girl/boy groups this turned out not to be necessary as everyone appeared comfortable in the larger group and there was some benefit in hearing different genders’ viewpoints.  Some of the young people talked about their relationships.  T talked about his girlfriend and expressed his hopes for the future.  M said that she had had a boyfriend at her previous school, but rarely saw him now.  The fact that we were prepared to talk about own teenage relationships increased their confidence in our integrity.  They seemed to greatly value the opportunity to talk about such an intimate and important subject.”

Mentor

The young people talked about what would cause most estrangement between them and their parents.  Issues that came up were:

- Getting pregnant (if you are a girl)  (For some of the boys getting a girl pregnant would be appalling, but for others, it would be seen as a sign that they are a real man).

- Taking drugs (both groups)

- Getting a tattoo

- Leaving home

A similar discussion with a group of young people who had been educated in an inclusive borough throughout produced different responses.  The boys seemed sure of their ability to attract girls and of their right to a sex life.  They expected to be able to have relationships with non-disabled girls and said that in the past people had been “very ignorant” but that these days it’s different.  The girls admitted to having had boyfriends and to an expectation of having several boyfriends before settling down.

“I think young disabled people in schools don’t see disabled adults.  I think it’s really good.  They were talking about sex and relationships that’s the sort of thing that wouldn’t happen here otherwise.”

Learning Support Service

###### 4.7 Development of Confidence and self-esteem.

Throughout the project we worked to develop the young people’s self-confidence and self esteem.  Regular activities included getting them to say what they liked about themselves and each other and to introduce themselves “loudly and proudly”.   At the beginning of the project this was very hard for some:

“We started with a round of your name, something you like about yourself and something you like about the person next to you.  This went well enough, they loved having something positive said about them.  There was lots of giggles and shyness and it was very hard to hear some of them.  I was glad of the BSL interpreter’s help.”

Mentor

However, as time went on, the young people became used to this activity and looked forward to it.

“One boy was very, very reserved and when he first came to the group he wouldn’t even come up to the table and he just drove his wheelchair round and round but eventually he got brave enough and he came over”

Teacher

One person in particular, who was barely audible at the start of the project, was able to speak out confidently about herself by the end.  Each session started with us asking them to tell us something that had happened since our previous meetings.

“One of the other children has very indistinct speech.  He is a child you don’t usually hear from but one day, I could just hear this boy talking at the top of his voice, and it was a wonderful feeling.”

Teacher

The young people became increasingly eager to confide in us, “

I think they really enjoy discussing things now and being able to talk about their feelings much more.”

Learning Support Services

Feedback we had from the young people was “You really listen.”  Listening well was very important.  Most young people with learning difficulties are used to not being listened to and display a degree of hopelessness and acceptance of it.  We made a particular point of showing that we were interested, that their viewpoint was relevant, that what they had to say was important and that they deserved to be listened to by us and by each other.

We attempted to model using good listening skills and made a requirement of the young people that they do the same.  By and large they were sympathetic and supportive of each other but there were some difficulties.  For instance, one young person had a huge yearning for a member of staff in the school.  The others in the group were irritated, dismissive and disrespectful of this.  A mentor reminded them that no matter how inappropriate the feelings and her expression of them might be, they were real feelings to her and she didn’t deserve to be laughed at or told off about them.  After that, group members became gentler with her around the issue and she became less insistent about displaying her feelings.

“I think there probably has been a change.  I think gradually young people in this group have got more confidence about things and a bit more open.”

Learning Support Service

##### 5.  Parents

5.1 We met with four sets of parents over the course of the project.  They were all very concerned about their young people and their futures.  One set of parents told us that they had had no idea their child had a learning difficulty before the educational psychologist diagnosed it.  To them she had always seemed, and continued to seem, as intelligent and able as her older sisters who are both at university.  They could not see any difference between her and them.

5.2 The parents were pleased to meet with disabled adults who had status and who were providing a role model for their young people.  They wanted to discuss the finer points of transition with us, although we were not really qualified to do this.  We worked mainly around the idea of not having closed expectations of their young people, pointing out that we know disabled adults with all sorts of qualifications (including people with learning difficulties who have degree level qualifications) and that what was true at one point in someone’s life would not necessarily be true at another.   Although there wasn’t enough time for this in the pilot project, more in depth work with parents would be beneficial.

##### 6.  School Staff

6.1 The mentors endeavoured to develop good working relationships with school staff and by and large this worked well.  Once the groups were established, we were welcomed into the schools and accommodated quite well.

“When I heard about it, I was so pleased.  We really need this kind of group for our students.  We feel we are working on our own - a bit isolated.  Any support we can get from outside is good. “

Teacher

6.2 Wherever possible, we made a point of being available to talk to staff before and after sessions and give them information (whilst respecting individual’s confidences) about what we had been doing with the young people.  Staff expressed appreciation of the work we were doing and reported that it was making a difference to have disabled people in the school.

“The work I do with young people is nothing like the work that can be done by someone who is disabled and who has been through the same experiences.”

Learning Support Service

“I wish it could always be here.  I hope it will be here for a long time in the future.  I do feel that if there is even one child that benefits from it, then it validates what is has done.”

Teacher

6.3 It was not always easy.  One group was disrupted several times because of school timetable changes; strikes; the bus arriving early; and health issues of mentors; etc.  Despite this, the group continued to function and grow.

6.4 Ratios of adults to young people needed to be high.  One group had two young Deaf people so a BSL interpreter was used,  one mentor brought a Personal Assistant - together with the three mentors, there was a total of five adults in the room.  We have found that every adult was needed and useful to the process.  Another group started with three adult mentors but went down to two, due to staff illness.  At one School, the ratio was two mentors to what started as three, and rose to eight, young people.   At Royal Docks, there were two mentors to four young people.  At another the ratio was one-to-one.  We had not realised how necessary this concentration of adults to young people would be but now understand that the intensity of the work fully requires this.

###### 7.  Promotion of Inclusion in the Schools

7.1 The original idea was to open the groups to disabled young people and their non-disabled friends.  We also envisaged having the groups outside of school time but eventually had to adjust this for all the groups due to problems involved in staying after school for the young people.  In the event, no non-disabled young people attended any of the groups.   Reasons for this included the timetabling of the groups by the schools as well the lack of non-disabled friends.

7.2 Despite the absence of non-disabled young people in the groups, the mentors quickly came to realise that there were real benefits in meeting as a disabled only group.  We worked towards helping disabled young people develop a sense of self-esteem and an awareness of their dignity and rights as disabled people.

“I think it’s been good for students to think about how included they are in the school and how they feel about it.”

Teacher

7.3 Had non-disabled young people been present, we consider it would have been more difficult to get them to open up about their real difficulties and issues.  There could, however, be valuable work done in schools with non-disabled young people around awareness raising, inclusion and disability equality.  Similar groups could be set up of non-disabled young people to examine their attitudes and practices around disabled classmates and friends.  It would be useful to challenge ideas about who gets to go out with who, who spends break times where, who talks to who in class, etc.

###### 8.  Conclusions and Recommendations

8.1 This has been a very worthwhile pilot project in terms of developing disability equality and promoting disabled young people’s rights and dignity in mainstream schools.   Our presence in the schools was very important to disabled young people.  Many had never met a disabled adult and had no idea that we are able to hold down jobs, earn good money and take a full part in the wider community.  One disabled adult has reported that when he was at school, the lack of disabled role models led him to believe that disabled people did not live until adulthood and that he could expect to die before reaching that stage himself.  Eight recommendations are outlined below:

##### 8.1 Continuation of the Project

All the schools we worked with supported the continuation of the project:

“I’d really like it to happen all the time – every week”

Young person

“It’s a starting point and it’s opened a lot of issues. “

Learning Support Service

“We need more regular sessions.  It would be good to have it ongoing every week.”

Teacher

“I hope it can go on because it’s hard work.  I think the young people didn’t realise what was involved.  It’s not easy but it would be a shame if it came to a stop.”

Learning Support Service

8.1.1 Recommendation Number One:

- That mentoring work using disabled mentors continues and is promoted and expanded to all schools.

It is important that mentors are drawn from the disabled community and that they have a strong identity as disabled people with a clear understanding of the social model of disability.

8.2 Working within the Education System

8.2.1 Establishing the Free Up Your Life groups proved to be much more problematic than we anticipated.  Although the Project was devised as a partnership arrangement between three London Boroughs and Disability Equality in Education, meetings with Senior LEA officials were hard to initiate and useful communication with the individual schools was even harder.  In an education service that is overworked and overstretched this is understandable and we appreciate that it was not from a lack of goodwill or intention, rather it was just sheer overload.

8.2.2 Despite strenuous efforts, we were unable to get anything other than an Assembly visit set up in one borough.  In September 2002 the borough was in a transition period – moving from being managed by a private company a trust.  It proved nigh on impossible to identify whom to target with information about the project.  There were many staff changes and people were not responsive to our publicity or telephone messages.  We did make contact and have meetings with head teachers and SENCOs at five different schools in the borough but were not able to negotiate the setting up of any groups.

8.2.3 Recommendation Number Two:

- That mentoring work with disabled young people in mainstream schools is taken on by the education service as part of its offer to the community.

It would be helpful to the project and to the young people if the schools were to ‘own’ the process themselves.  We had to overcome people’s prejudice about visitors coming into the school and applying our vision.  If the vision and the mentors were directly employed by the school there would be a more respectful response to the project generally and to the work we set out to do.

##### 8.3 Raising Disability Equality in Education Awareness

8.3.1 We were surprised at the level of misunderstanding of disabled issues shown by some staff.  For instance, one school told us that they never mentioned the word “disabled” because they didn’t want to upset the young people.  This meant that we had to do a large amount of work on promoting the social model of disability in order to get young people to understand the issues at all.  If staff had an understanding of this, it would help promote inclusion.

“We probably need to make the rest of the school more aware.  It takes a long time to do awareness raising.  We need to do more of it.  We need to keep going.  We need people to come in more regularly.”

Teacher at George Green’s School

8.3.2 Recommendation Number Three:

- Disability Equality in Education Training for all school staff and students.  Increased awareness raising activities for the schools generally.

While all schools we worked with could adopt the description of ‘inclusive’, there is a lack of understanding of the continual restructuring of policies, practices and procedures that is necessary to include disabled pupils in the academic and social life of the school to meet their fullest possible potential.

##### 8.4 Staffing

8.4.1 We were under-prepared for the difficulties that arose for some mentors working with disabled young people in mainstream schools.  A primary goal was for the mentors to form relationships with young people.  One or two mentors found it hard to prioritise the forming of relationships over producing solid outcomes in terms of paper-based tasks, etc.  One mentor became very depressed as he recognized his own issues in the young people and realized that, far from resolving them, he had merely put them behind him.  Going to the school regularly was bringing him face to face with things he preferred not to think about.

Recommendation Number Four:

- In any future similar project, mentors should receive regular 1:1 supervision.  This should include counselling around their feelings with regard to the work.

##### 8.5 Coordinator Post

8.5.1 The one-day-a-week spent on coordinator time was inadequate.  The coordination of such a complex project involves liaison with a wide range of agencies, staff, mentors, young people, parents, etc. and it is not realistic to run the project without at least one full time member of staff.

Recommendation Number Five:

- A full-time co-ordinator is appointed to each Borough.  The appointment might be able to come under Learning Support Services or the Connexions Service.

##### 8.6 Flexible arrangements for time with young people

8.6.1 As young people got used to us, they tried to deal with some of the painful issues in their lives.   Sometimes the issues were not easily dealt with in a large group.  For instance, one young man had had a series of deaths in his family and wanted to talk about it.  He needed to be listened to for a long time but there was inadequate time available for this in a large group where everybody had to share the attention.

Recommendation Number Six:

- That 1:1 time is set aside to follow up issues that have been raised in the larger group

##### 8.7 School Staff Interventions in Mentoring Sessions

8.7.1 Some mentors were disturbed by what they saw of the relationships between staff and students.  More than once, we witnessed young people being pushed, pulled and told off.  Initially we felt that staff was worried about being shown up by ‘bad’ behaviour on the part of the young people.  In some groups, this was quickly resolved when the mentors made it clear that they were able to deal with whatever came up.  In others, it was an ongoing problem, with teaching assistants, etc. monitoring the groups and intervening as they saw fit.  Ideally, it would be better if school staff members were not in the room during sessions but this leads onto issues of ratios of adults to young people.

Recommendation Number Seven:

- That mentoring groups are staffed at a ratio of at least two mentors for every four children

Recommendation Number Eight:

- That school staff do not intervene unless it is absolutely essential.  This will help to build trust and respect between the disabled mentors and disabled young people.

Christine O’Mahony

Disability Equality in Education

March 2003

# Footnotes

See Appendix 1 for details of activities involved in setting up and delivering the programme.

See inside front cover

see inside page cover

see inside front cover for example of publicity

See front and back covers

see inside back cover

See inside back cover

see inside front cover

see inside front cover

# Text boxes

My hopes and dreams